## Instructions
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Start Date.
Define a standard unit of measure for all extimates (hours, days, dollars, etc)
For each estimate complete the following:
A | Estimator Name: This column should be populated with the name of the individual providing the estimate
B | Description of Activity Being Estimated: This column should be populated with a description of the schedule activity being estimated
C | Estimate Date: This column should be populated with the date that the estimate was performed.
D | Best Case Estimate: This column should be populated with an estimate that is based on the best-case scenario for work completion
E | Most Likely Estimate: This column should be populated with an estimate that, given the resources available to do the work, is the most realistically expected
F | Worst Case Estimate: This column should be populated with an estimate that is based on the worst-case scenario for work completion
G | Weighted Average Estimate: This column is automatically calculated using a mathematical formula to determine a weighted average of the three types of estimates and uses the formula (Estimate=[Optimistic+[4*Most Likely]+Pessimistic]/6) to calculate that weighted average estimate.
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on. From the file menu click "Date" -> "Filter" ->"Auto Filter". Then select your filter criteria from the drop down menu that appears on your header cell.

## Estimate
Project Estimate
Refer to the CDC_UP_Microsoft_Project_Practices_Guide.doc for additional information on estimating.
Project Name:
National Center:
Project Manager Name:
Project Start Date:
|  |  |  | Total Weighted Work Estimate = |  | 494.1667
Estimator Name | Description of Activity Being Estimated | Estimate Date | Best Case Estimate | Most Likely Estimate | Worst Case Estimate | Weighted Average Estimate
Individual 1 | Product functionality (1) | 2001-01-01 | 100 | 150 | 300 | 166.6667
Individual 2 | Product functionality (2) | 2001-01-02 | 95 | 135 | 250 | 147.5
Individual 3 | Product functionality (3) | 2001-01-03 | 115 | 160 | 325 | 180
Note on A10: Estimator Name: This column should be populated with the name of the individual providing the estimate
Note on B10: Description of Activity Being Estimated: This column should be populated with a description of the schedule activity being estimated
Note on C10: Estimate Date: This column should be populated with the date that the estimate was performed.
Note on D10: Best Case Estimate: This column should be populated with an estimate that is based on the best-case scenario for work completion
Note on E10: Most Likely Estimate: This column should be populated with an estimate that, given the resources available to do the work, is the most realistically expected
Note on F10: Worst Case Estimate: This column should be populated with an estimate that is based on the worst-case scenario for work completion
Note on G10: Weighted Average Estimate: This column is automatically calculated using a mathematical formula to determine a weighted average of the three types of estimates and uses the formula (Estimate=[Optimistic+[4*Most Likely]+Pessimistic]/6) to calculate that weighted average estimate.